# COCOMO II Estimation Assignment

Student Attendance Management System (SAMS) CSE, Jahangirnagar University

#### Complete Solution: Parts (a)–(g)

Basis: The supplied assignment case study specifies a 30 KLOC web-based Student Attendance Management System and provides the COCOMO II ratings to be used for estimation.

## Appropriate COCOMO II Model

Selected model: COCOMO II Post-Architecture. The project has a preliminary SRS, estimated size, product and database characteristics, performance requirements, team information, development approach/site/schedule information, and detailed ratings for scale factors and effort multipliers. Therefore, Post-Architecture is the appropriate model for this assignment. The assignment also explicitly requires Post-Architecture for the effort calculation.

| Model | Decision |
| --- | --- |
| Application Composition | Not selected |
| Early Design | Not selected |
| Post-Architecture | Selected |

## COCOMO II Parameter Identification

### Scale Factors

| Scale Factor | Rating | Value |
| --- | --- | --- |
| PREC – Precedentedness | Nominal | 3.72 |
| FLEX – Development Flexibility | Nominal | 3.04 |
| RESL – Architecture/Risk Resolution | High | 3.29 |
| TEAM – Team Cohesion | Nominal | 3.29 |
| PMAT – Process Maturity | Nominal | 4.68 |

SF = 3.72 + 3.04 + 3.29 + 3.29 + 4.68 = 18.02

### Effort Multipliers

| Effort Multiplier | Rating | EM |
| --- | --- | --- |
| RELY – Required Reliability | High | 1.10 |
| DATA – Database Size | Nominal | 1.00 |
| CPLX – Product Complexity | Nominal | 1.00 |
| RUSE – Developed for Reusability | Low | 1.07 |
| DOCU – Documentation | Nominal | 1.00 |
| TIME – Time Constraint | Nominal | 1.00 |
| STOR – Storage Constraint | Nominal | 1.00 |
| PVOL – Platform Volatility | Low | 1.00 |
| ACAP – Analyst Capability | Nominal | 1.00 |
| PCAP – Programmer Capability | Nominal | 1.00 |
| APEX – Application Experience | Nominal | 1.00 |
| PLEX – Platform Experience | Nominal | 1.00 |

| Effort Multiplier | Rating | EM |
| --- | --- | --- |
| LTEX – Language/Toolset Experience | Nominal | 1.00 |
| PCON – Personnel Continuity | Nominal | 1.00 |
| TOOL – Software Tools | High | 0.90 |
| SITE – Multisite Development | High | 0.93 |
| SCED – Required Schedule | Nominal | 1.00 |

EAF = 1.10 × 1.07 × 0.90 × 0.93 = 0.985149  0.985

## Development Effort

COCOMO II Post-Architecture effort equation:

PM = A × SizeE × EAF

A = 2.94; Size = 30 KLOC; E = 1.0902; EAF = 0.985149

PM = 2.94 × 301.0902 × 0.985149

PM  118.09 person-months

## Exponent and Scale Interpretation

E = B + 0.01 × SF

E = 0.91 + 0.01 × 18.02 = 1.0902

Since E is greater than 1, the project exhibits diseconomies of scale. Under the assumed project characteristics, effort grows more than proportionally as software size increases.

## Development Schedule

TDEV = C × PMF

F = D + 0.2(E  B)

F = 0.28 + 0.2(1.0902  0.91) = 0.31604

TDEV = 3.67 × 118.090.31604  16.58 months

Estimated development schedule: approximately 16.6 months, or about 1 year and 5 months.

## Approximate Average Staffing Requirement

Average Staff = Effort / Schedule

Average Staff = 118.09 / 16.58  7.12 persons

Therefore, the approximate average staffing requirement is 7 people. This is an average staffing estimate rather than a fixed team size for every project phase.

## SRS-Change Impact Analysis

The assignment asks how six possible changes to the SRS would affect COCOMO II factors and whether the estimated effort would generally increase or decrease.

| SRS Change | Likely Factor(s) | Effect on Effort | Reason |
| --- | --- | --- | --- |
| 1. Concurrent users: 500  2,000 | CPLX, TIME, possibly RELY | Increase | Higher load and scalability needs can require more complex architecture |
| 2. Very high reliability | RELY | Significant increase | More fault tolerance, validation, testing, recovery and reliability assurance |
| 3. Add biometric attendance | CPLX, APEX, RELY; Size | Increase | Introduces biometric hardware/software integration, processing, security. |
| 4. Add mobile applications | Size, CPLX, APEX, PLEX | Substantial increase | Adds mobile application development, APIs, device compatibility, UI/UX |
| 5. Increase audit/security require | CPLX, RELY, DOCU | Increase | Requires stronger access control, encryption |
| 6. Reduce schedule by 20% | SCED | Increase effort | Schedule compression generally raises pressure |

,

### Schedule-compression calculation for change 6

Current schedule = 16.58 months

Reduced schedule = 16.58 × 0.80 = 13.26 months

Thus, a 20% schedule reduction would target approximately 13.26 months, while the corresponding SCED pressure would generally increase the effort required.

## Final Results — Parts (a)–(g)

| Parameter | Final Result |
| --- | --- |
| Model | COCOMO II Post-Architecture |
| Software Size | 30 KLOC |
|  Scale Factors | 18.02 |
| Exponent E | 1.0902 |
| EAF | 0.985149  0.985 |
| Development Effort | 118.09 person-months |
| Development Schedule | 16.58 months |
| Average Staffing | 7.12  7 persons |
| Scale Behavior | Diseconomies of scale |
| SRS Changes | All six changes generally increase effort; schedule compression |